## Gantt Chart
|  |  |  | November 2024' | [16 empty] | December 2024 | [30 empty] | January 2025' | [30 empty] | February 2025 ' | [27 empty] | March 2025' | [30 empty] | April 2025' | [29 empty] | May 2025' | [30 empty] | June 2025' | [29 empty] | July 2025' | [30 empty] | August 2025'
Activity | Description | Resource | Status | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Input TIFF files and metadata into MongoDB | TIFF files- Fluorescent Images , metadata- XLS1 –well location cell name and treatment ,XLS2 | Shani, Ofir | Not Started
Segmentation-tracking parameters | Using CellProfiler | Shani, Ofir | Not Started
Compare CellProfiler segmentation outputs | Compare outputs using Imaris- The Gold standard | Shani, Ofir | Not Started
Optimize segmentation-tracking parameters | Optimize based on the comparison to Imaris | Shani, Ofir | Not Started
Input the finel segmentation output into pyBatch. | The goal - to extract 50 morphokinetic features and creat Morphokinetic analysis data | Shani, Ofir | Not Started
Establish and optimize LSTM. | LSTM-based clustering parameters for analyzing sarcoma cells morphokinetic data. | Shani, Ofir | Not Started
Compare LSTM model with existing LSTM model | Existing LSTM model from Github | Shani, Ofir | Not Started
Study morphokinetic time-series groups/subgroups | Finel Goal of the project | Shani, Ofir | Done
Gantt Chart Submission |  | Shani, Ofir | Not Started
Gantt presentation Backup |  | Shani, Ofir | Not Started
First Report Submission |  | Shani, Ofir | Not Started
First Presentations Session |  | Shani, Ofir | Not Started
Abstract Submission |  | Shani, Ofir | Not Started
Final Project Submission